## S9.2
ATCO Electric Yukon (AEY)
2023 - 2024 General Rate Application (GRA)
Continuity of Capital Expenditures
($000)
Variance
Line |  | Business | Actuals |  | Approved |  | $ | %
No. | Project Name | Case | 2016 | 2017 | 2016 | 2017 | 2016-2017
1 | Generation
2 | Fish Lake 2 Head Pond Spillway Replacement |  | 286.1399 | 165.6556 | 20 | 589 | 157.2046 | 34.8% | Delayed to 2018 due to Fish Lake Ditch 1 Failure as well as digging and water level conditions.
3 | Fish Lake Ditch 1 Failure | #02 | 412.0702 | -150.1965 | 0 | 0 | -261.8737 | -100% | Unanticipated event that required immediate remediation. 2017 includes $150K credit for insurance proceeds. Please see Business Case #02 for further details.
4 | Fish Lake Ditch 1 Intake Building - Design |  | 2.0437 | 0.87023 | 0 | 30 | 27.0861 | 929.5%
5 | Fish Lake Unit 1 Spillway Diversion Structure |  | 0 | 30.1853 | 0 | 411 | 380.8147 | 1262% | Delayed to 2019 and 2020 due to Fish Lake Ditch 1 Failure as well as digging and water level conditions.
6 | Fish Lake Unit 2 Assessment |  | 97.8229 | 11.2684 | 100 | 0 | -9.0913 | -8.334%
7 | Fish Lake Water Monitoring Upgrades |  | 9.963 | 106.4611 | 25 | 25 | -66.4242 | -57.05% | Higher than approved due to Fish Lake Ditch 1 Failure and changes in requirements.
8 | Fish Lake Unit 1 Turbine and Building Replacement |  | 19.5904 | 15.7282 | 0 | 0 | -35.3186 | -100%
9 | Fish Lake Ditch 3 Diversion Replacement |  | 2601.256 | 167.647 | 2908 | 0 | 139.0971 | 5.024%
10 | Louise Lake Containment Dyke Seismic Analysis |  | 0 | 0 | 40 | 0 | 40 | 100%
11 | Watson Lake Plant Fire Alarm System - Design |  | 0 | 0 | 0 | 102 | 102 | 100% | The costs related to the project design were captured in the Watson Lake Plant Fire alarm project in line 12 below and were lower than expected.
12 | Watson Lake Plant Fire Alarm System |  | 0 | 61.8295 | 0 | 0 | -61.8295 | -100% | Higher than approved due to costs related to project design being included in this line item ($7K) as well as project work being advanced from future years.
13 | Watson Lake Plant PLC |  | 0 | 27.819 | 0 | 0 | -27.819 | -100%
14 | Watson Lake Unit 5 PLC |  | 0 | 22.2397 | 0 | 0 | -22.2397 | -100%
15 | Watson Lake Unit 2 Replacement |  | 1053.8832 | 270.1477 | 1387 | 0 | 62.9692 | 4.756%
16 | Old Crow Unit 2 Generator Refurbishment |  | 39.0948 | 0 | 75 | 0 | 35.9052 | 91.84%
17 | Old Crow Original Plant Rebuild | #41 | 369.4105 | 49.7664 | 0 | 249 | -170.1769 | -40.6% | Higher than approved due to unexpected costs required to reinforce the floor of the facility. 2018 includes a $118K credit for settlement costs from the Engineering firm hired to design the new plant due to the failure of the floor system design. Costs related to the original plant rebuild were incurred from 2018 through 2022.
18 | Old Crow Unit 3 Replacement |  | 1085.0683 | 8.0678 | 1046 | 0 | -47.1361 | -4.312%
19 | Old Crow Unit 2 - External Equipment |  | 0 | 0 | 0 | 51 | 51 | 100% | Lower than approved due to work on project being halted based on plant conditions. Awaiting new plant construction.
20 | Destruction Bay Unit 1 Major Overhaul | #23 | 132.9347 | 7.3046 | 0 | 0 | -140.2392 | -100% | Units require an overhaul after 24,000 hours of runtime, which occurred earlier than anticipated for Destruction Bay Unit 1. Please see Business Case #23 for further details.
21 | Destruction Bay Unit 3 Replacement |  | 5.2869 | 28.2489 | 0 | 0 | -33.5358 | -100%
22 | Destruction Bay Programmable Logic Controller Upgrade |  | 14.7009 | 252.0541 | 0 | 305 | 38.245 | 14.34%
23 | Destruction Bay Unit 2 Replacement |  | 537.5736 | 8.7693 | 620 | 0 | 73.6571 | 13.48% | Lower than approved due to shared savings of other work being completed on site PLC replacement line 22.
24 | Destruction Bay Fuel Line Upgrade |  | 54.7582 | 0 | 106 | 0 | 51.2418 | 93.58% | Lower than approved due to forecast including costs for potential Utilidor and plant modifications which where not required during construction.
25 | Pelly Crossing Fuel System Upgrade |  | 0 | 142.9211 | 0 | 152 | 9.0789 | 6.352%
26 | Pelly Crossing Ventilation System Upgrade |  | 0 | 0 | 0 | 25 | 25 | 100%
27 | Pelly Crossing Unit 2 Silencer |  | 0 | 0 | 0 | 20 | 20 | 100%
28 | Ross River Replace ABB 5HK Breakers |  | 71.3819 | 0 | 95 | 0 | 23.6181 | 33.09%
29 | Ross River Electrical Service Panel Upgrade |  | 0 | 0 | 25 | 0 | 25 | 100%
30 | Swift River Unit 1 Replacement |  | 36.4326 | 82.3124 | 80 | 61 | 22.255 | 18.74%
31 | Teslin Plant Assessment |  | 0 | 12.5883 | 0 | 102 | 89.4117 | 710.3% | Lower than approved due to project scope being reduced to only assess pad and foundation.
32 | Teslin PLC Replacement - Design |  | 0 | 41.1486 | 0 | 105 | 63.8514 | 155.2% | Lower than approved due to project scope being increased to include long lead equipment purchase.
33 | Haines Junction Fuel Containment Upgrade |  | 0 | 0 | 0 | 30 | 30 | 100%
34 | PLC Replacement Stage 1 |  | 0 | 75.9684 | 0 | 103 | 27.0316 | 35.58%
35 | 2017 Gen Failed Hardware Contingency |  | 0 | 27.4883 | 0 | 0 | -27.4883 | -100%
36 | Mobile Generator 250kW Voltage and Frequency Protection |  | 6.9884 | 0.2739 | 35 | 0 | 27.7377 | 381.9%
37 | Mobile Generator 225 kW Refurbishment |  | 5.5369 | 10.3807 | 20 | 0 | 4.0824 | 25.65%
38 | Mobile Generator 350 kW Refurbish Enclosure |  | 0 | 38.377 | 0 | 19 | -19.377 | -50.49%
39 | Fuel System Assessment |  | 0 | 0 | 0 | 99 | 99 | 100% | Work was complete in 2017, but due to the scope of work, it was determined that the expenses should be classified as O&M instead of capital.
40 | IRC Chargers |  | 0 | 0 | 0 | 22 | 22 | 100%
41 | Generation < $20,000 |  | 102.1737 | -552.8055 | 20 | 29 | 499.6319 | -110.9% | Lower than approved due to cancelled project write-offs, including a $443K write-off of for Watson Lake LNG per Board Order 2017-03 in 2017.
42
43 | Generation Total |  | 6944.1106 | 962.5195 | 6602 | 2529 | -1224.3699