## S9.2
ATCO Electric Yukon (AEY)
1 | Variance of the actual to 2016-17 approved expenditures is less than 100 percent and $100,000. | 2023 - 2024 General Rate Application (GRA)
2 | 2018-2022 expenditures are under $100,000.
3 | 2023-2024 expenditures are under $500,000 | Continuity of Capital Expenditures - Clean
4 | No individual project over $100,000 in any year | ($000)
5 | Contributed project, expenditures net of contributions lower than thresholds
Line |  |  | Actuals | [6 empty] | Test Period |  | Approved
No. | Project Name | Business Case Reference | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2016 | 2017
1 | Generation
2 | Fish Lake Unit 2 - Replace Power Station - Detailed Design | Business Case No. 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 527.36 | 0 | 0
3 | Fish Lake 1 Roof Replacement | Business Case No. 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452.0646 | 0 | 0 | 0
4 | Fish Lake 2 Replace Power Station FEED | Business Case No. 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0
5 | Fish Lake 2 Head pond Intake Building Replacement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.3186 | 0 | 0 | 0
6 | Fish Lake 2 Head Pond Spillway Replacement | 1 | 286.1399 | 165.6556 | 539.7302 | -17.3279 | 0 | 0 | 0 | 0 | 0 | 20 | 589
7 | Fish Lake Ditch 1 Failure | Business Case No. 02 | 412.0702 | -150.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Fish Lake Ditch 1 Intake Building - Design | 1 | 2.0437 | 0.87023 | 114.6351 | -25.9355 | 11.1162 | 0 | 0 | 0 | 0 | 0 | 30
9 | Fish Lake Unit 1 Spillway Diversion Structure | 1 | 0 | 30.1853 | 0.25355 | 220.0729 | 526.9129 | -5.4748 | 0 | 0 | 0 | 0 | 411
10 | Fish Lake Unit 2 Assessment | 1 | 97.8229 | 11.2684 | -111.7225 | 0 | 0 | 0 | 0 | 34.8433 | 0 | 100 | 0
11 | Fish Lake Unit 2 Condition Assessment and Options Analysis | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 66.1692 | 0 | 0 | 0 | 0
12 | Fish Lake 2 TIV actuator and wicket gates | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.0797 | 0 | 0 | 0
13 | Fish Lake Unit 1 Roof Design | Business Case No. 32 | 0 | 0 | 0 | 0 | 0 | 43.2834 | 15.5165 | 0 | 0 | 0 | 0
14 | Fish Lake Unit 2 Bearing and Shaft Repair | 2 | 0 | 0 | 0 | 47.8181 | 5.6296 | 0 | 0 | 0 | 0 | 0 | 0
15 | Fish Lake Unit 2 TIV Replace | 2 | 0 | 0 | 48.0546 | -0.74476 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Fish Lake 1 Add TIV Actuator | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.53 | 0 | 0
17 | Fish Lake 1 TIV replacement | 2&3 | 0 | 0 | 0 | 0 | 0 | 0 | 23.8143 | 88.9288 | 0 | 0 | 0
18 | Fish Lake 2 Add bypass valve actuator and automation | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0
19 | Fish Lake 2 PLC Replacement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.934 | 0 | 0
20 | Fish Lake Unit 2 DC TIV Actuator & Wicket Gate Replacement | AEY-YUB-046(b) Attachment 2 | 0 | 0 | 0 | 0 | 0 | 0 | 138.1954 | 0 | 0 | 0 | 0
21 | Fish Lake Water Monitoring Upgrades | 1,2&3 | 9.963 | 106.4611 | 0.65282 | 24.139 | -0.055907 | -0.005277 | 0 | 25.8196 | 81.37 | 25 | 25
22 | Fish Lake Unit 1 Turbine and Building Replacement | 2 | 19.5904 | 15.7282 | 15.8674 | 3.0719 | 3.8007 | 2.9777 | -70.6391 | 0 | 0 | 0 | 0
23 | Fish Lake Ditch 3 Diversion Replacement | 1 | 2601.256 | 167.647 | 30.2038 | 0.0056218 | 0 | 29.3806 | -27.2907 | 0 | 0 | 2908 | 0
24 | Louise Lake Containment Dyke Seismic Analysis | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0
25
26 | Watson Lake - Replace Air Start Piping | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102.5 | 0 | 0 | 0
27 | Watson Lake Add Building Concrete Apron | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
28 | Watson Lake block heater pumps | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0
29 | Watson Lake Expansion Tank and Access Replacement Design | 2&3 | 0 | 0 | 0 | 0 | 0 | 0 | 25.3583 | 152.4805 | 0 | 0 | 0
30 | Watson Lake Fuel Piping Upgrade | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230.5562 | 0 | 0 | 0
31 | Watson Lake Fuel System Control Replacement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.8813 | 0 | 0 | 0
32 | Watson Lake Install Diverter Actuator, with limit switches, for #1/6 boilers | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
33 | Watson Lake Replace HRS pumps/motors | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.4163 | 0 | 0 | 0
34 | Watson Lake Replace Non-Code Exchangers for #2/4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.2082 | 0 | 0 | 0
35 | Watson Lake Unit 1 Replacement | Business Case No. 07 | 0 | 0 | 0 | 418.4198 | 1278.2491 | 130.3364 | 0 | 0 | 0 | 0 | 0
36 | Watson Lake Unit 2 - Major Overhaul | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0
37 | Watson Lake Unit 3 Replacement | Business Case No. 07 | 0 | 0 | 435.6917 | 1212.67 | 240.9244 | 0 | 0 | 0 | 0 | 0 | 0
38 | Watson Lake Unit 4 - Major Overhaul | Business Case No. 23 | 0 | 0 | 371.0193 | -2.0409 | 0 | 0 | 0 | 0 | 515 | 0 | 0
39 | Watson Lake Unit 4 EMCP Replacement | Business Case No. 08 | 0 | 0 | 0 | 0 | 0 | 176.6202 | -25.5424 | 0 | 0 | 0 | 0
40 | Watson Lake Unit 5 Major Overhaul | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 0 | 438.0641 | 41.3377 | 0 | 0 | 0
41 | Watson Lake Unit 6 Replacement | Business Case No. 07 | 0 | 0 | 0 | 0 | 828.3825 | 900.8985 | 140.34 | 0 | 0 | 0 | 0
42 | Watson Lake Waste Heat Cathodic Protection | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0
43 | Watson Lake 125VDC Battery and Charger Replacement | 2 | 0 | 0 | 0 | 22.6888 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Watson Lake Fuel Tank Access | Reference Document 1 | 0 | 0 | 16.6233 | 128.2277 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Watson Lake Inverter Replacement | 2 | 0 | 0 | 0 | 51.0174 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Watson Lake Plant Fire Alarm System - Design | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Watson Lake Plant Fire Alarm System | 1 | 0 | 61.8295 | 105.7692 | -1.8489 | 0 | 0 | 0 | 0 | 0 | 0 | 102
48 | Watson Lake Plant Fuel Sys Control Replace | 1 | 0 | 0 | 0 | 0 | 0 | 1.1004 | 147.3306 | 0 | 0 | 0 | 99
49 | Watson Lake Plant Overhead Door Replacement | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 23.7927 | 0 | 0 | 0 | 0
50 | Watson Lake Plant Phone System Replacement | 2 | 0 | 0 | 0 | 34.4982 | -0.62668 | 0 | 0 | 0 | 0 | 0 | 0
51 | Watson Lake Plant PLC | 2 | 0 | 27.819 | 0.91081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | Watson Lake Unit 5 PLC | 2 | 0 | 22.2397 | 0.72814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Watson Lake Utilidor Split/Fuel Sys | 2 | 0 | 0 | 42.4925 | 6.4501 | 4.0724 | 2.3121 | 2.5317 | 0 | 0 | 0 | 0
54 | Watson Lake Unit 2 Replacement | 1 | 1053.8832 | 270.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1387 | 0
55
56 | Old Crow Add Day Tank and Fuel Transfer Pump | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 103 | 0 | 0
57 | Old Crow Boiler Metering and Control | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
58 | Old Crow Plant Tank Access | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231.75 | 0 | 0
59 | Old Crow Unit 1 Major Overhaul YTCU414 | Business Case No. 23 | 0 | 0 | 0 | 0 | 474.6531 | -9.7131 | 0 | 0 | 0 | 0 | 0
60 | Old Crow Unit 2 Replacement | AEY-YUB-046(b) Attachment 1 | 0 | 0 | 0 | 191.9078 | -17.0688 | 0 | 0 | 0 | 0 | 0 | 0
61 | Old Crow Unit 3 Failure - Major Overhaul | 2 | 0 | 0 | 0 | 0 | 0 | 269.7316 | -189.9874 | 0 | 0 | 0 | 0
62 | Old Crow Unit 4 Major Overhaul | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 0 | 252.2328 | 0 | 0 | 0 | 0
63 | Old Crow # 2 Long Block Replacement | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5183 | 0 | 0 | 0 | 0
64 | Old Crow Unit 2 Generator Refurbishment | 1 | 39.0948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0
65 | Old Crow Old Plant Gantry Accessories | 2 | 0 | 0 | 0 | 0 | 22.7987 | -1.6629 | 0 | 0 | 0 | 0 | 0
66 | Old Crow Plant (old) Gantry Crane | 2 | 0 | 0 | 0 | 0 | 22.2241 | 0 | 0 | 0 | 0 | 0 | 0
67 | Old Crow Original Plant Rebuild | Business Case No. 41 | 369.4105 | 49.7664 | -117.7112 | 2.3888 | 5.6376 | 489.0137 | -84.8033 | 149.63 | 0 | 0 | 249
68 | Old Crow Unit 3 Replacement | 1 | 1085.0683 | 8.0678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046 | 0
69 | Old Crow Unit 2 - External Equipment | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
70
71 | Beaver Creek Unit 3 Major Overhaul | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 323.4114 | -5.8628 | 0 | 0 | 0 | 0
72 | Beaver Creek Replace JW and CAC cooler | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
73 | Beaver Creek Station Service Transformer | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
74 | Beaver Creek Unit 1 Major Overhaul | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 306.5909 | -131.9616 | 0 | 0 | 0 | 0
75 | Beaver Creek Unit 2 Major | Business Case No. 23 | 0 | 0 | 127.1132 | -1.2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | Beaver Creek Utilidor Upgrades | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0
77 | Destruction Bay/ Stewart/ Beaver Creek Plant Condition Assessment | Business Case No. 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.7543 | 0 | 0 | 0
78
79 | Destruction Bay Unit 2 Major Overhaul | Business Case No. 23 |  | 0 | 0 | 0 | 0 | 181.2514 | -7.3175 | 0 | 0 | 0 | 0
80 | Destruction Bay Unit 1 Major Overhaul | Business Case No. 23 | 132.9347 | 7.3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | Destruction Bay Unit 3 Replacement | 1 | 5.2869 | 28.2489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | Destruction Bay Programmable Logic Controller Upgrade | 1 | 14.7009 | 252.0541 | 13.0099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305
83 | Destruction Bay Unit 2 Replacement | 1 | 537.5736 | 8.7693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620 | 0
84 | Destruction Bay Fuel Line Upgrade | 1 | 54.7582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 0
85 | Destruction Bay Unit 3 Major Overhaul | Business Case No. 23 | 0 | 0 | 0 | 0 | 0 | 111.5221 | -15.692 | 0 | 0 | 0 | 0
86 | Destruction Bay Replace POW | Business Case No. 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0
87
88 | Pelly Crossing Fuel System Upgrade | 1 | 0 | 142.9211 | 119.4991 | -3.5773 | 0 | 0 | 0 | 0 | 0 | 0 | 152
89 | Pelly Crossing Ventilation System Upgrade | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
90 | Pelly Crossing Unit 2 Silencer | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
91
92 | Ross River Replace ABB 5HK Breakers | 1 | 71.3819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 0
93 | Ross River Electrical Service Panel Upgrade | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0
94
95 | Swift River Unit 2 Replacement | Business Case No. 21 | 0 | 0 | 0 | 0 | 0 | 0 | 224.5889 | 2.1717 | 0 | 0 | 0
96 | Swift River Unit 1 Replacement | 1 | 36.4326 | 82.3124 | 4.0934 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 61
97 | Swift River Fuel System Upgrade | 2 | 0 | 0 | 0 | 37.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Swift River Unit 1 PLC Replacement | 2 | 0 | 0 | 0 | 23.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | Swift River Unit 2 Replace | 2 | 0 | 0 | 0 | 0 | 52.3418 | 7.8774 | 0 | 0 | 0 | 0 | 0
100
101 | Teslin Plant Assessment |  | 0 | 53.7368 | -14.431 | 1.2016 | 0 | 0 | 0 | 0 | 0 | 0 | 102
102 | Teslin PLC Replacement - Design | Reference Document 2 | 0 | 0 | 386.68 | -0.93744 | 0 | 0 | 0 | 0 | 0 | 0 | 105
103 | Teslin Plant Platform Replacement | 2 | 0 | 0 | 0 | 33.9418 | -0.10909 | 0 | 0 | 0 | 0 | 0 | 0
104 | Teslin Rad Core Replacement | 2 | 0 | 0 | 0 | 0 | 21.7176 | 0 | 0 | 0 | 0 | 0 | 0
105
106 | Haines Junction Fuel Containment Upgrade | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
107 | Haines Junction Plant Positive Air Shutoff for YTCU416 | 1 | 0 | 0 | 0 | 0 | 0 | 19.8087 | 2.891 | 0 | 0 | 0 | 0
108 | Haines Junction Regulator Pad Replacement | 1 | 0 | 0 | 0 | 0 | 0 | 4.4398 | 36.2034 | 0 | 0 | 0 | 0
109
110 | Louise Lake Auxiliary Structure Replacement | Business Case No. 33 | 0 | 0 | 0 | 11.2157 | 31.197 | 7.5013 | 2.307 | 0.77658 | 772.5 | 0 | 0
111
112 | IPP Remote monitoring | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
113 | Carmacks Plant Foundation Repair | 2 | 0 | 0 | 0 | 14.0319 | 16.1458 | 0 | 0 | 0 | 0 | 0 | 0
114 | Mobile CUL-341 PLC replacement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.0905 | 0 | 0
115 | Pelly Unit 3 Block Replacement | Business Case No. 23 | 0 | 0 | 0 | 110.9181 | -1.2415 | 0 | 0 | 0 | 0 | 0 | 0
116 | PLC Replacement Stage 1 | 1 | 0 | 75.9684 | -2.8294 | -0.73654 | 0 | 0 | 0 | 0 | 0 | 0 | 103
117 | Replace fuel ESD valve within utilidor (x10) | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5 | 0 | 0
118 | 2017 Gen Failed Hardware Contingency | 2 | 0 | 27.4883 | -0.98154 | -2.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | Mobile Generator 250kW Voltage and Frequency Protection | 1 | 6.9884 | 0.2739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0
120 | Mobile Generator 225 kW Refurbishment | 1 | 5.5369 | 10.3807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
121 | Mobile Generator 350 kW Refurbish Enclosure | 1 | 0 | 38.377 | 2.1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
122 | Standby plant equipment and building heat | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5 | 0 | 0
123 | Add transfer trip scheme | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
124 | Fish Creek Diversion | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.24 | 0 | 0
125 | General Plant Improvements | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.5 | 0 | 0
126 | Fuel System Assessment | 1 | [9 empty] | 0
127 | IRC Chargers | 1 | [9 empty] | 0 | 22
128
129 | Generation < $20,000 | 4 | 102.1737 | -552.8055 | 19.3168 | 96.0017 | 70.0951 | 59.0698 | 126.8844 | 82.3325 | 51.5 | 20 | 29
130
131 | Generation Total |  | 6944.1106 | 962.5195 | 2146.7693 | 2635.0691 | 3596.7967 | 3050.2716 | 1177.6418 | 3723.0996 | 3351.7745 | 6602 | 2529
132
133 | Kluane First Nation Wind Turbine Upgrades | Business Case No. 37 | 0 | 0 | 0 | 0 | 12.1498 | 17.483 | 1210.1934 | 2215.0366 | 749.84 | 0 | 0
134 | Renewables - Old Crow | 5 | 0 | 0 | 0 | 1033.9828 | 1147.334 | 1405.5074 | 33.5478 | 0 | 0 | 0 | 0
135 | Watson Lk IPP - Integration to Plant | 2&3 | 0 | 0 | 0 | 0 | 0 | 17.7683 | 5.7423 | 75.2862 | 0 | 0 | 0
136 | Beaver Creek PV Generation | Business Case No. 38 | 0 | 0 | 0 | 0 | 0 | 64.3097 | 2500.1218 | 3766.692 | 1686.11 | 0 | 0
137 | Study Costs | 1,2&3 |  | 208 | 80 | -27 | -72 | -175 | -1 | -13
138 | Renewables Total |  | 0 | 208 | 80 | 1006.9828 | 1087.4838 | 1330.0684 | 3748.6053 | 6044.0148 | 2435.95 | 0 | 0
139
140
141 | New Extensions
142 | New Services Overhead and Underground | Reference Document 3 & Business Case No. 18 | 1908.4442 | 1702.5022 | 2555.1514 | 2701.4765 | 2445.7262 | 3664.7945 | 2776.8095 | 4218.7453 | 4324.214 | 1995 | 2032
143 | Annual Land Rights | 1,3&4 | 115.5342 | 83.868 | 65.6079 | 88.8227 | 81.2786 | 69.2375 | 67.276 | 101.7334 | 82 | 120 | 122
144 | General Drafting and Mapping | 1,3&4 | 37.4655 | 34.5675 | 53.392 | 42.4053 | 51.9239 | 48.6614 | 45.2111 | 45.7567 | 41 | 40 | 41
145
146 | Whistle Bend Stage 3 | Business Case No. 31 | 215.1633 | 690.4052 | 544.518 | 479.3386 | -19.5692 | 0 | 0 | 0 | 0 | 0 | 1521
147 | Whistle Bend Stage 4 | Business Case No. 31 | 0 | 475.5789 | 729.1944 | 717.1802 | -11.5251 | 0 | 0 | 0 | 0 | 0 | 0
148 | Whistle Bend Stage 5 | Business Case No. 31 | 0 | 0 | -16.844 | 745.0688 | 215.8327 | 0 | 0 | 0 | 0 | 0 | 0
149 | Whistle Bend Stage 6 | Business Case No. 31 | 0 | 0 | 0 | 0 | 433.4283 | 0 | 0 | 285.1597 | 0 | 0 | 0
150 | Whistle Bend Stage 7 | Business Case No. 31 | 0 | 0 | 0 | 0 | 8.8609 | 0.13644 | 350.5216 | 460.3341 | 0 | 0 | 0
151 | Whistle Bend Stage 8 | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 140.4637 | 17.8418 | 0 | 0 | 0
152 | Whistle Bend Stage 9 | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683.2103 | 458.35 | 0 | 0
153 | Whistle Bend future stages - place holder | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0
154 | Whistle Bend New Services |  | 0 | 0 | 0 | 0 | 136.1137 | 0 | 234.2538 | 0 | 0 | 0 | 0
155
156 | Mt Sima Pumphouse | 5 | 0 | 0 | 0 | 0 | 122.9892 | 141.0895 | 0 | 0 | 0 | 0 | 0
157 | Brookside Phase 2B | 5 | 0 | 112.3879 | 58.7948 | 25.4484 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | Challenge Development 704 Main Street | 5 | 0 | 0 | 0 | 0 | 135.2828 | 0.19572 | 0 | 0 | 0 | 0 | 0
159 | Hammerstone Lots off Tlingit Street | 5 | 0 | 0 | 0 | 0 | 36.8342 | 26.7238 | 124.5104 | 0 | 0 | 0 | 0
160 | Loft 2240 2nd Avenue | 5 | 0 | 0 | 0 | 0 | 0 | 133.1702 | 0 | 0 | 0 | 0 | 0
161 | Mt Sima Hill Service | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 412.7921 | 0 | 0 | 0 | 0
162 | Schmidt, Harold & Savanah | 5 | 0 | 0 | 0 | 119.2331 | -1.1512e-16 | 0 | 0 | 0 | 0 | 0 | 0
163 | TSL/Ketza Old Crow Health & Housing | 5 | 0 | 0 | 0 | 0 | 0 | 162.5988 | 0 | 0 | 0 | 0 | 0
164 | VGFN Houses on North Rd | 5 | 250.3656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | VoT Connector Road Subdivision | 5 | 0 | 0 | 0 | 144.5549 | -0.73232 | 0 | 0 | 0 | 0 | 0 | 0
166
167 | YG Airport Hangar | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 561.9076 | -29.8884 | 0 | 0 | 0
168 | Yukon Lot 503 | 5 | 0 | 0 | 0 | 112.6352 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169
170 | New Extension < $20,000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102.182 | 0 | 0 | -1
171 | New Extensions Total |  | 2526.9728 | 3099.3097 | 3989.8146 | 5176.1636 | 3636.4438 | 4246.6077 | 4713.7457 | 5885.0748 | 5214.564 | 2155 | 3715
172
173
174 | New Extensions-IPP
175 | Arctic Pharm IPP | Business Case No. 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 543.4347 | 0 | 0 | 0
176 | Sunergy YEC HJ IPP | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343.3497 | 0 | 0 | 0
177 | Haeckel Hill | Business Case No. 36 | 0 | 0 | 0 | 0 | 0 | 0 | 1219.226 | 235.2955 | 0 | 0 | 0
178 | NOMAD IPP | 5 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0
179 | SOLVEST IPP | 5 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0
180 | THELP | 5 | 0 | 0 | 0 | 0 | 0 | 184.9179 | 174.5551 | -7 | 0 | 0 | 0
181 | New Extensions - IPP Total |  | 0 | 0 | 0 | 0 | 0 | 365.9179 | 1393.7811 | 1115.0799 | 0 | 0 | 0
182
183 | Distribution Improvements
184 | Annual Right of Way Widening | Business Case No. 12&26 | 494.3914 | 580.5971 | 291.9225 | 489.2243 | 433.9885 | 480.9832 | 555.1904 | 520 | 528.39 | 439 | 447
185 | General Pole Replacements | 1,3&4 | 40.3991 | 35.1053 | 38.8234 | 28.9261 | 112.3176 | 97.2557 | 97.5609 | 254.4472 | 211.15 | 297 | 284
186 | PCB Identification and Transformer Change Outs | 1 | 136.8352 | 14.3736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 51
187 | Vault Replacements | 1 | 27.4536 | 43.7158 | 0.38969 | 116.9604 | -14.8807 | -3.642 | 9.845 | 51.25 | 0 | 40 | 102
188 | General Clearance Upgrades/Fixes | 1,3&4 | 11.0517 | 0 | 5.2082 | 3.4865 | 8.8277 | 33.0783 | 36.7359 | 84.161 | 108.15 | 50 | 51
189 | Test and Treat Pole Program | 3&4 | 0 | 0 | 0 | 45.2629 | 25.4204 | 69.7966 | 116.6965 | 20.5 | 21.63 | 0 | 0
190 | Gang Switch Replacement | 1,3&4 | 53.2915 | 28.9159 | 11.379 | 35.7221 | 18.5948 | 1.0085 | 20.2656 | 0 | 0 | 0 | 0
191 | T&B Switch Change Out | 1,3&4 | 17.3368 | 2.0867 | 19.881 | 36.3671 | 32.0786 | 34.4853 | 16.4426 | 119.2579 | 63.86 | 0 | 0
192
193 | McIntyre Subdivision Rebuild | Business Case No. 01 | 747.6756 | 1035.0568 | 405.3712 | 141.2973 | -91.2517 | 1368.3151 | 284.9652 | 108.9421 | 1244.24 | 564 | 924
194 | Downtown Whitehorse Capacity Upgrade | 1 | 1298.6727 | 507.0105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1451 | 366
195 | Hillcrest Subdivision Conversion | 1 | -4.7858 | 41.2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152
196
197 | Upgrade Underground Line Into Services and Shipyard Sub | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | McCrae Substation Second Feeder Breaker | 1 | 307.834 | 133.3143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 0
199 | McCrae Substation Transformer Upgrade to 10 MVA | 1 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 0
200 | Whistle Bend Way Underground Crossing | 1 | 68.5155 | -7.812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0
201 | Upper Liard – Replace Liard River Crossing | 1 | 27.4067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | AEY 34.5kV Cable Replacement | 1 | 151.7034 | 0.1211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0
203 | Fault Indicators in Padmount Equipment | 1 | 48.8628 | 0.63395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0
204 | AEY Maintenance Work Request 241-2016 HJ Reg | 1 | 22.9344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | AEY 2016 Safety Audit F | 1 | 22.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | AEY Cable Testing 2016 | 1 | 20.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | AEY Maintenance Work Request M97-2013 Pole Change | 1 | 2.2119 | 25.7178 | 0.20729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | AEY 102 Lambert Encroachment | 1 | 2.1129 | 2.7724 | 2.3165 | 18.2709 | 1.2875 | 1.6294 | 1.3398 | 0 | 0 | 0 | 0
209 | AEY 102 Lambert Encroachment | 1 | 1.385 | 66.7817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 5L622 - Lewes River Bridge Crossing Replacement | 1 | 0.79575 | 86.6905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0
211 | Paint Mountain Conductor Replacement | 1 | -3.5682 | 144.0754 | 72.028 | 306.075 | 36.6399 | 176.9797 | -33.5738 | 0 | 0 | 0 | 559
212 | Range Road Rebuild | 1 | 107.6662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0
213 | Carcross Nares Bridge Relocation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
214 | [9 empty] | 0 | 0 | 0 | 0
215 | Replace Watson Lake Substation Transformer T2 | 1 | 0 | 174.8311 | 66.7518 | -6.9422 | 0.10406 | 0 | 0 | 0 | 0 | 0 | 356
216 | 400 Amp Regulators in Logan Substation | Business Case No. 03 | 0 | 167.9463 | 5.6929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
217 | AEY Carcross Corner Pol | 1 | 0 | 40.9481 | 0.7644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | AEY Maintenance Work Order M255-2016 3rd a | 1 | 0 | 28.1859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | AEY CCC Rd Rebuild | Reference Document 4 | 0 | 9.1413 | 173.7341 | 0.087114 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 3 Phase Hotsprings Rd | Business Case No. 05 | 0 | 0 | 0 | 386.3658 | 11.1842 | -3.6146 | 0 | 0 | 0 | 0 | 0
221 | Haines Junction OSS Replacement | 1 | 0 | 46.9074 | 20.7111 | -16.473 | 0 | 0 | 0 | 0 | 0 | 0 | 51
222 | Single Regulator 5L631 | 1 | 0 | 25.1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
223 | Steward Crossing Ferry Hill Line Rebuild - Design | 1 | 0.21205 | 15.7909 | 1.574 | 0.93227 | 0.9563 | -20.9128 | 0 | 0 | 0 | 0 | 30
224 | McRae Substation Regulator Upgrade | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
225 | Rebuild Line Behind City Municipal Services Building | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
226
227
228 | Distribution Improvements Continued
229 | AEY Old Crow Volt Issues-Loop | Reference Document 5 | 0 | 0 | 356.1579 | 5.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | AEY 25kV A.Hwy Hamilton Tie | Business Case No. 11 | 0 | 0 | 217.9631 | -11.6536 | -13.5391 | 0 | 0 | 0 | 0 | 0 | 0
231 | McIntyre Subdivision Contingency Loop | Business Case No. 11 | 0 | 0 | 115.6395 | 189.3293 | -0.36555 | -9.592 | 0 | 0 | 0 | 0 | 0
232 | Teslin Substn Metering | 2 | 0 | 0 | 61.4418 | -0.82959 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | Teslin OSS Replacement | 2 | 0 | 0 | 47.1058 | -0.23004 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | AEY 3rd Ave Burial Dwntwn | 2 | 0 | 0 | 42.3404 | 2.5386 | 5.8294 | 2.1359 | 2.3388 | 0 | 0 | 0 | 0
235 | AEY Wtsn Lk Vertical Strcts | 2 | 0 | 0 | 27.5947 | 0.013861 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | AEY Teslin Sub Gnd Grid | 2 | 0 | 0 | 18.0498 | 7.302 | 6.2172 | 0.12698 | 0 | 0 | 0 | 0 | 0
237 | AEY Lower Post Fire 2018 | 2 | 0 | 0 | 16.3466 | 23.5537 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | AEY Cowley Rd Rebuild SKH | Reference Document 6 | 0 | 0 | 7.4428 | 84.7856 | 18.1221 | 0 | 0 | 0 | 0 | 0 | 0
239 | AEY 2nd Ave Trespass | 2 | 0 | 0 | 3.1742 | 1.9995 | 18.3263 | 0 | 0 | 0 | 0 | 0 | 0
240 | AEY SCADA Swtch at Pinerdg | 2 | 0 | 0 | 1.4597 | 42.2552 | 2.1575 | 24.6529 | 6.4323 | 0 | 0 | 0 | 0
241 | YG Toyota Access, Intersection & Frontage Road Upgrades | 5 | 0 | 0 | 0.35649 | 341.3186 | 1.9718 | 0 | 0 | 0 | 0 | 0 | 0
242 | AEY YG Nares River Bridge | 2 | 3.6006 | 82.0183 | -12.8542 | -7.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | Whitehorse Airport Hanger D Area Rebuild | 2 | 0.19385 | 11.6667 | 0.89726 | 159.6312 | -9.03 | 0 | 0 | 0 | 0 | 0 | 142
244
245 | AEY Reroute Mountain View | 2 | 0 | 0 | 0 | 53.2454 | 2.878e-17 | 0 | 0 | 0 | 0 | 0 | 0
246 | AEY Aerial Trespass Lot 9 Blk 16 Adela Trail Watson Lake | Reference Document 7 | 0 | 0 | 0 | 0.047884 | 1.4613 | 115.87 | 37.1923 | 0 | 0 | 0 | 0
247 | Rogers Street 25kV Conversion | 2 | 0 | 0 | 0 | 23.5273 | 15.5321 | 0 | 0 | 0 | 0 | 0 | 0
248 | AEY Trespass Primary Line Reroute, Lot 1499 Hotsprings Road | 2 | 0 | 0 | 0 | 0.8123 | 20.8597 | 24.3583 | 0 | 0 | 0 | 0 | 0
249 | Install 35kV Regulators on Carcross Road | Business Case No. 17 | 0 | 0 | 0 | 0 | 199.3241 | -2.9369 | 0 | 0 | 0 | 0 | 0
250 | HLC Breaker Replacement | Business Case No. 04 | 0 | 0 | 0 | 0 | 135.5578 | 0 | 0 | 0 | 0 | 0 | 0
251 | Upgrade Regulators at Laberge Substation | Business Case No. 09 | 0 | 0 | 0 | 0 | 129.108 | 0 | 0 | 0 | 0 | 0 | 0
252 | Powerline Relocation Hillcrest YG Highway Realignment | Business Case No. 15 | 0 | 0 | 0 | 0 | 118.9554 | 4.8237 | -2.9836 | 0 | 0 | 0 | 0
253 | Reconductor Mayo Rd Mainline | Business Case No. 06 | 0 | 0 | 0 | 0 | 110.5117 | 0 | 0 | 0 | 0 | 0 | 0
254 | Shipyards Sub Replace Relays | 2 | 0 | 0 | 0 | 0 | 93.501 | 0 | 0 | 0 | 0 | 0 | 0
255 | 266 ACSR Upgrade Sumanik Drive | 2 | 0 | 0 | 0 | 0 | 73.1748 | 0 | 0 | 0 | 0 | 0 | 0
256 | AEY Aerial Trespass Lots 14A & 14B Pilot Mtn Sub'd | 2 | 0 | 0 | 0 | 0 | 37.3428 | 0 | 0 | 0 | 0 | 0 | 0
257 | AEY D/C Powerline Reroute Cousins to Mayo Cutoff | 2 | 0 | 0 | 0 | 0 | 34.654 | -7.0304 | 0 | 0 | 0 | 0 | 0
258 | Riverdale Load Sectionalizing | 2 | 0 | 0 | 0 | 0 | 24.576 | 0 | 0 | 0 | 0 | 0 | 0
259 | DWCI -Downtown South Voltage Conversion- prep | 2 | 0 | 0 | 0 | 0 | 17.4156 | 18.3978 | 1.6377 | 0 | 0 | 0 | 0
260 | AEY Reconductor Mayo Road Mainline - Stage 2 | Business Case No. 06 | 0 | 0 | 0 | 0 | 14.6053 | 137.5977 | 0 | 0 | 0 | 0 | 0
261 | AEY Powerline Relocation YG Alaska Hwy Crestview Phase 1 of 2 | Business Case No. 15 | 0 | 0 | 0 | 0 | 0.1938 | 225.0102 | -40.9767 | 0 | 0 | 0 | 0
262
263 | Powerline Relocation Burns Road to Range Road Intersection | Business Case No. 15 | 0 | 0 | 0 | 0 | 0 | 135.6148 | -17.5478 | 0 | 0 | 0 | 0
264 | AEY Hamilton to Alaska Highway 25kV Tie | 2 | 0 | 0 | 0 | 0 | 0 | 72.8477 | -4.0135 | 0 | 0 | 0 | 0
265 | AEY Powerline Relocation Lot 2 Salvation Army | 2 | 0 | 0 | 0 | 0 | 0 | 61.7883 | 2.3894 | 0 | 0 | 0 | 0
266 | Upgrade Recloser at Carx Substn | 2 | 0 | 0 | 0 | 0 | 0 | 44.1791 | 0 | 0 | 0 | 0 | 0
267 | AIS 9 Switch Cube Replacement - S2350 Hamilton Blvd | 2 | 0 | 0 | 0 | 0 | 0 | 36.6489 | 0.33004 | 0 | 0 | 0 | 0
268 | AEY New Subst Mayo Rd | 2 | 0 | 0 | 0 | 0 | 0 | 29.0572 | 0 | 0 | 0 | 0 | 0
269 | AEY Voltage Issues Gold Road | 2 | 0 | 0 | 0 | 0 | 0 | 2.873 | 28.1463 | 0 | 0 | 0 | 0
270
271 | AEY Aerial Trespass Lot 23, Blk 25 or 102 Teslin Crescent, (Thomas Slager), Watson Lake | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 46.9907 | 0 | 0 | 0 | 0
272 | Ross River Substn Voltage Regulator Control | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 35.7765 | 0 | 0 | 0 | 0
273 | Upgrade Recloser Mountainview Substn | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 54.4043 | 0 | 0 | 0 | 0
274 | New Substation Mayo Road | Business Case No. 25 | 0 | 0 | 0 | 0 | 0 | 0 | 399.5423 | 2400 | 0 | 0 | 0
275 | Reconductor Mayo Rd Mainline - Stage 3 | Business Case No. 06 | 0 | 0 | 0 | 0 | 0 | 0.15691 | 161.9752 | 0 | 0 | 0 | 0
276 | Watson Lake Substation Feeder & Feeder Protection Replacement | Reference Document 8 | 0 | 0 | 0 | 0 | 0 | 0 | 146.2261 | 65.6582 | 0 | 0 | 0
277
278 | Downtown south voltage conversion |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | AEY Choutla Long Span Rebuild | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
280 | AEY Dogwood voltage improvement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0
281 | AEY DWCI - New 12.5kV substation | Note 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 792.07 | 0 | 0
282 | AEY Haines Junction Regulator Stand Replacement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0
283 | AEY New Substation Whistle Bend - Leota | Business Case No. 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.75 | 2781 | 0 | 0
284 | AEY Nisultlin Bridge Pole Relocation | Note 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 164.8 | 0 | 0
285 | AEY SCADA Pineridge Switch | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.1002 | 0 | 0 | 0
286 | AEY Upgrade 6L11 conductor S150 to Carcross Corner | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 51.5 | 0 | 0
287 | AEY Upgrade recloser | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.125 | 89.61 | 0 | 0
288 | AEY Voltage Improvement Destruction Bay | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0
289 | AEY Whitehorse Escarpment line reroutes - Hoge | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0
290 | Robinson sub capacity | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.8 | 0 | 0
291 | AEY Hillcrest Voltage Improvement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
292 | AEY Pelly Crossing Voltage Improvement | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360.5 | 0 | 0
293 | Watson Lake 5L621 Upgrade | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0
294 | Power System Assessment - YEC and AEY | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 206 | 0 | 0
295 | Whitehorse CKES UG conversion | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.5 | 0 | 0
296 | Encroachment 3rd and Black Encroachment | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.6 | 0 | 0
297
298 | AEY 6L19 voltage improvement | Business Case No. 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593.28 | 0 | 0
299 | Relocate 100 A Carcross Cutoff Regulator | Business Case No. 30 | [8 empty] | 178
300 | Relocate 100 A Lewes River Regulator | Business Case No. 30 | [8 empty] | 178
301 | AEY Carcross PQ monitoring | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.25 | 0 | 0
302 | AEY Whitehorse Escarpment line reroutes - 5th avenue | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 0 | 0
303 | Old Crow voltage improvement - reconductor | Business Case No. 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 463.5 | 0 | 0
304
305 | 400 Amp Regulators in Arkell Substation | 1 | 0 | 160.5501 | 5.4422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122
306 | Shipyards Spare 25kV Breaker | 1 | 0 | 55.0085 | 146.3358 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 102
307 | Replace Underground Cables at Whitehorse Airport | 1 | 0.048469 | 0.70698 | 0.52682 | 0.068494 | -0.20798 | 0.053503 | -1.2691 | 0 | 0 | 0 | 84
308 | Distribution Improvements < $20,000 |  | 196.7146 | 259.8724 | 145.5482 | 130.2457 | 26.6841 | 28.2384 | 66.119 | 142.6553 | 10.3 | 81 | 77
309 | Distribution Improvements Total |  | 4103.3484 | 3819.1546 | 2317.7242 | 2633.6691 | 1658.2065 | 3180.2345 | 2028.1782 | 5194.8469 | 9081.13 | 4335 | 4153
310
311 | Street and Sentinel Lighting
312 | General Streetlight Replacements | 4 | 237.44 | 210.9696 | 85.3439 | 166.4296 | 47.9761 | 104.6836 | 121.1513 | 341.8853 | 186.43 | 199 | 254
313 | New Customer Streetlight Installations | Business Case No. 34 | 169.8191 | 112.0049 | 230.2599 | 84.4079 | 849.5301 | 555.1707 | 179.6561 | 1060 | 448.05 | 199 | 203
314 | Whistle Bend Streetlights | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | Watson Lake Street Light Replacement |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
316 | St Lt Replacements Hart Cr. | Business Case No. 20 | 0 | 0 | 0 | 0 | 0 | 180.1757 | 0 | 0 | 0 | 0 | 0
317 | Car Cross Streetlights | 5 | 0 | 428.5288 | -23.595 | 110.5483 | -0.017974 | 0 | 0 | 0 | 0 | 0 | 0
318
319 | Alaska Highway North Klondike Highway Intersection | 5 | 0 | 0 | 0 | 0 | 359.4905 | 0.17207 | 0 | 0 | 0 | 0 | 0
320 | Street Lights Burns Road to Range Road Intersection | 5 | 0 | 0 | 0 | 0 | 0 | 184.1107 | 0 | 0 | 0 | 0 | 0
321 | Street Lights Lodestar to Philmars Phase 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 508.5643 | 0 | 0 | 0 | 0
322 | Pelly Crossing Community Lights | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 144.9015 | 0 | 0 | 0 | 0
323 | [11 empty] | 0 | 0
324 | McIntyre Subdivision Streetlight Rebuild | Business Case No. 01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411.5567 | 154.5 | 175 | 254
325 | YG Nisutlin Bridge Streetlights | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 106.09 | 0 | 0
326
327 | Whistle Bend 3C Street Lights | 5 | 0 | 184.8622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | Whistle Bend Lights 4D | Business Case No. 31 | 0 | 0 | 0 | 0 | 159.1993 | 0 | 0 | 0 | 0 | 0 | 0
329 | Whistle Bend Street Lights - Stage 4 | Business Case No. 31 | 0 | 0.052113 | 260.5659 | 290.5168 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | Whistle Bend Street Lights - Stage 5 | Business Case No. 31 | 0 | 0 | 0 | 132.9768 | 211.0684 | 0 | 0 | 0 | 0 | 0 | 0
331 | Whistle Bend Street Lights - Stage 6 | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50.2957 | 0 | 0 | 0
332 | Whistle Bend Street Lights - Stage 7 | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 30.9246 | 55.1279 | 300.5297 | 0 | 0 | 0
333 | Whistle Bend Street Lights - Stage 8 | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102.5 | 0 | 0 | 0
334 | Whistle Bend Street Lights - Stage 9A | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0
335 | Whistle Bend Street Lights - Stage 9B | Business Case No. 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.29 | 0 | 0
336
337 | Street and Sentinel Lighting < $20,000 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 25
338 | Street and Sentinel Lighting Total |  | 407.2591 | 936.4175 | 552.5746 | 784.8794 | 1627.2465 | 1055.2375 | 1009.4011 | 2562.7674 | 1042.36 | 584 | 777
339
340 | Meters
341 | AMI Project New Meters | AEY-YUB-065(a) Attachment 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131.6974 | 304 | 0 | 0
342 | Replacement of Meters and New Installations | 1,2,3&4 | 104.5733 | 88.1812 | 31.9791 | 67.42 | 126.6081 | 75.2913 | 97.7051 | 102.9463 | 106.09 | 199 | 203
343 | Meters Total |  | 104.5733 | 88.1812 | 31.9791 | 67.42 | 126.6081 | 75.2913 | 97.7051 | 234.6437 | 410.09 | 199 | 203
344
345 | Transformers & Regulators
346 | General Capitalizable Transformers | Business Case No. 16 | 0 | 0 | 0 | 0 | 267.5715 | 48.6952 | -18.7862 | 217.8404 | 275.01 | 90 | 91
347 | Spare 10 MVA Transformer | 1 | 250.9305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219 | 0
348 | Spare Padmount Regulator for Shipyards Substation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0
349 | Transformers and Regulators | 4 | 72.9909 | 212.8662 | 69.5027 | 262.064 | 117.7098 | 173.2414 | 10.3667 | 0 | 0 | 0 | 0
350 | AEY Old Crow Regulators | Business Case No. 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0
351 | Transformers & Regulators Total |  | 323.9215 | 212.8662 | 69.5027 | 262.064 | 385.2813 | 221.9367 | -8.4195 | 927.8404 | 275.01 | 367 | 91
352
353 | GP&E
354 | Computer
355 | My Account- Technology Project | Business Case No. 19 | 0 | 0 | 21.7515 | 247.4187 | -3.549 | 0 | 0 | 0 | 0 | 0 | 0
356 | Computer Total |  | 0 | 0 | 21.7515 | 247.4187 | -3.549 | 0 | 0 | 0 | 0 | 0 | 0
357
358 | Land & Building
359 | Service Complex Heating System | 1 | 3.6151 | 17.2757 | 5.7489 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 25
360 | Annual Building Upgrades | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4472 | 73.13 | 0 | 0
361 | Downtown Office Interior Renovations | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.25 | 0 | 0 | 0
362 | Whitehorse Service Complex RTU'S Construction | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
363 | Whitehorse Service Complex Rooftop Unit Design | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3941 | 0 | 0 | 0
364 | Service Complex Boiler Replacement | Business Case No. 10 | 0 | 0 | 0 | 0 | 132.2908 | -27.3732 | 0 | 0 | 0 | 0 | 71
365 | Kilowatt - Misc. Imp | 1 | 24.1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 102 Kilowatt Ln Refurbish | 1&2 | 0 | 14.1331 | 32.1874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 101 Kilowatt Ln Refurbish | 1&2 | 0 | 19.3365 | 32.1874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | Warehouse Mezzanine Upg | 1 | 0 | 21.7873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | DT Office Renos & Improvements | 2 | 0 | 0 | 0 | 26.9881 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | Service Complex Yard Extension | 2 | 0 | 0 | 0 | 36.0055 | 0.29526 | 0 | 0 | 0 | 0 | 0 | 0
371 | Fencing for Marwell Yard | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 44.6892 | 0 | 0 | 0 | 0
372 | Old Crow Bunkhouse replacement | Business Case No. 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0
373 | Fish Lake 1 Storage building roof replacements | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.25 | 0 | 0
374 | Downtown Office Security and Fire Suppression | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0
375 | Warehousing Seacan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.75 | 0 | 0
376 | Furnace Replacements - Watson Lake | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0
377 | Watson Lake Septic Upgrade | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
378 | Watson Lake Storage Solutions | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92
379 | Land & Buildings - Corporate < $20,000 | 4 | 60.8556 | 32.3262 | 20.745 | 8.7057 | 14.7248 | 4.9484 | 50.3192 | 0 | 0 | 0 | 0
380 | Total Land & Buildings |  | 88.6371 | 104.8588 | 90.8687 | 71.6993 | 147.3108 | -22.4248 | 95.0083 | 232.0913 | 794.13 | 65 | 239
381
382
383 | Communication Equipment
384 | Communication Equipment | 1,2,3&4 | 36.3105 | 22.735 | 2.3277 | -0.364 | 19.4371 | 48.1056 | -46.0146 | 0 | 0 | 18 | 13
385 | AEY SCADA Upgrades | 4 | 26.3653 | 115.5943 | 30.0347 | 20.1967 | 9.6521 | 5.1394 | 20.2801 | 47.457 | 141.11 | 49 | 66
386 | Satellite Radios | Business Case No. 14 | 0 | 0 | 0 | 0 | 0 | 0 | 156.5089 | 0 | 0 | 0 | 0
387 | Windows XP Conversion for Operations Dispatch | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0
388 | Form 6 Substation Controls | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0
389 | Whitehorse SCADA Dispatch UHF Repeater | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
390
391 | Total Communication Equipment |  | 62.6757 | 138.3293 | 32.3623 | 19.8327 | 29.0893 | 53.245 | 130.7745 | 47.457 | 141.11 | 117 | 115
392
393 | Tools, Instruments & Equip.
394 | FRC Replacement | 1,2,3&4 | 18.7561 | 24.2172 | 9.2297 | 17.5602 | 12.546 | 9.9713 | 7.9719 | 22.2187 | 24.72 | 0 | 0
395 | Power Quality Meter | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 14.1524 | 20 | 0 | 0 | 0
396 | Primary current monitors | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26.78 | 0 | 0
397 | Miscellaneous Tools and Instruments | 4 | 132.3435 | 138.2737 | 63.5494 | 179.7198 | 95.1058 | 150.0029 | 64.592 | 241.9243 | 76.22 | 149 | 165
398 | Total Tools, Instruments & Equip. |  | 151.0996 | 162.4909 | 72.7791 | 197.28 | 107.6518 | 159.9741 | 86.7163 | 310.1431 | 127.72 | 149 | 165
399
400 | Office Computer Equipment
401 | Office Furniture & Equipment | 1,2,3&4 | 20.4032 | 11.316 | 1.5606 | 5.2736 | 4.9564 | 12.4303 | 14.4898 | 62.1456 | 20 | 20 | 20
402 | 2021 Surface Pro Purchases | 2 | 0 | 0 | 0 | 0 | 0 | 21.042 | 0 | 0 | 0 | 0 | 0
403 | Replace XP Operating Systems - iFix PCs | 1 | 31.4079 | 0.362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46
404
405 | GP&E Continued
406 | CIS Replacement | Business Case No. 22 | 0 | 0 | 0 | 0 | 0 | 680.2739 | 3712.3034 | 3666.2335 | 345.05 | 0 | 0
407 | Asset Management - Evaluation & Program Roadmap | 2&3 | 0 | 0 | 0 | 0 | 0 | 0 | 59.4165 | 13.0375 | 0 | 0 | 0
408 | Asset Management - Phase 1 | Business Case No. 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 901.25 | 0 | 0
409 | Sales force | AEY-YUB-066(b) Attachment 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.6792 | 154.5 | 0 | 0
410 | My Account Enhancements - AEY | 2 | 0 | 0 | 0 | 0 | 0 | 37.0955 | 15.5448 | 0 | 0 | 0 | 0
411 | Enterprise Batch Printing | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8204 | 0 | 0 | 0 | 0
412 | Fleet Maximo - AEY | 2 | 0 | 0 | 23.6896 | 29.3608 | 6.9645 | 0 | 0 | 0 | 0 | 0 | 0
413 | Oracle R12 Replacement | Note 3 | 0 | 51.3909 | 50.9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414
415 | Office Computer Equipment < $20,000 | 4 | 2.1415 | 15.5267 | 2.8366 | 9.7161 | 20.5739 | 4.0475 | -70.838 | 42.6668 | 12.7308 | 0 | 0
416 | Total Office Computer Equipment |  | 53.9526 | 78.5955 | 78.9868 | 44.3505 | 32.4949 | 754.8892 | 3779.7369 | 4260.7625 | 1433.5308 | 20 | 66
417
418 | Transportation Equipment
419 | Transportation Equipment | Business Case No. 27&28 | 17.6101 | 294.4438 | 6.2691 | 88.0611 | 117.2257 | 506.6205 | 396.7942 | 696.5378 | 766.0625 | 369 | 315
420 | Purchase New Unit YT169 - Small Bucket Truck | Business Case No. 13 | [6 empty] | 264.2126
421 | Unit 136 to Replace Unit 643 Bucket Truck | AEY-YUB-041(a)(viii) Attachment 1. |  | 370.833
422 | Unit YT144 New Mechanic's Truck | Business Case No. 13 | 0 | 0 | 0 | 144.6153 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | Purchase Unit YT145 to Replace Unit 091 | Business Case No. 13 | 0 | 0 | 0 | 149.0242 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | Unit 151 Digger to Replace Unit 429 - WLk Bucket | Business Case No. 13 | 0 | 0 | 0 | 0 | 324.0355 | 10.9397 | 0 | 0 | 0 | 0 | 0
425 | Purchase Unit YT148 - Replace Unit 092 - Ram 5500 CC 4x4 - Flat Deck | Business Case No. 13 | 0 | 0 | 0 | 0 | 128.5343 | 0 | 0 | 0 | 0 | 0 | 0
426 | Purchase YT159 - Replace Unit 886 - 1 Ton Service Body | Business Case No. 13 | 0 | 0 | 0 | 0 | 0 | 157.8132 | 0 | 0 | 0 | 0 | 0
427 | Total Transpiration Equipment |  | 17.6101 | 665.2768 | 6.2691 | 381.7005 | 569.7955 | 675.3734 | 661.0068 | 696.5378 | 766.0625 | 369 | 315
428 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | Other Projects Less Than $20,000 | [10 empty] | 37 | 102
430 | GP&E Total |  | 373.9751 | 1149.5513 | 303.0176 | 962.2817 | 882.7932 | 1621.057 | 4753.2428 | 5546.9916 | 3262.5533 | 757 | 1002
431 | Grand Total |  | 14784.1606 | 10476 | 9491.3822 | 13528.5297 | 13000.8599 | 15146.6225 | 18913.8816 | 31234.359 | 25073.4318 | 14999 | 12470
432
433 | Note 1: The project is not going into service in test period and therefore will not impact rate base or revenue requirement. A business case will be completed upon completion of the engineering study.
434 | Note 2: This was a government directed pole movement, AEY is mandated to abide by these requests, no business case was completed as a result.
435 | Note 3: This project has since been retired and no longer in ratebase no ratebase or revenue requirment impact.